## Entire Team
Item Description | 2025-08-25
Complete SU 1 Slides |  | In Progress
SU Presention Run-Through |  | Not Started | Not Started
Status Update 1 Presentation |  |  | Due Date
Write FSR |  | Not Started | Not Started | Due Date
Write ICD |  | Not Started | Not Started | Due Date
Create Validation Plan |  | In Progress | In Progress | Due Date
ECEN Design Blitz | [11 empty] | Due Date | Due Date
Complete SU 2 Slides | [13 empty] | Not Started | Not Started | Not Started
SU Presention Run-Through | [14 empty] | Not Started | Not Started
Status Update 2 Presentation | [16 empty] | Due Date
Complete SU 3 Slides | [17 empty] | Not Started | Not Started | Not Started
SU Presentation Run-Through | [18 empty] | Not Started | Not Started
Status Update 3 Presentation | [20 empty] | Due Date
Finial Report Due | [21 empty] | Due Date
Mobile App/Enclosure |  | In Progress | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
DAQ/Microcontrollers |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
FPGA/Memory |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
Power/Filtering |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started

## MobileEclosure
Item Description | 2025-08-25
Finalize front-end AWG tab |  | Not Started
Finialze front-end drawable tab |  | Not Started
Draft Enclosure Design |  | Not Started | Not Started
Finalize app front-end polish for AWG & Drawable tabs
Define backend stubs (simulate frequency, amplitude, offset changes); Draft initial enclosure design sketches
Connect sliders/inputs to backend variables (simulate output values); Select enclosure dimensions & layout
Add backend 'Send' function (test with mock data); Build rough enclosure CAD model
Simulate waveform plotting with backend-calculated points; Review enclosure CAD with team
Establish simple test communication with microcontroller (send dummy values); Choose LEDs, ports, buttons
Implement backend offset and waveform type handling (simulate); Update CAD with chosen components
Test microcontroller receives values correctly (basic UART/Bluetooth/WiFi message); Prepare enclosure CAD for 1st print
Expand app backend to handle drawable waveform → array output (simulation only); Order enclosure hardware
Add error handling in app; Print enclosure prototype V1
Debug app backend simulations; Fit hardware into prototype enclosure
Add UI usability polish; Revise CAD for enclosure V2
Subsystem test: app sends values → microcontroller receives/logs; Print enclosure V2
Add waveform preset save/load feature in app; Assemble enclosure V2 and test usability
Subsystem test: app backend + microcontroller (values only); Refine enclosure details
Fix latency/data transmission issues at subsystem level; Prepare final enclosure CAD V3
Stress test app; Print/machine final enclosure
Document subsystem testing results (app + microcontroller); Assemble final enclosure build
Freeze app features (bug fixes only); Paint/finish final enclosure
Verify subsystem-level communication with microcontroller; Document enclosure build process
Polish app UI/UX; Wire LEDs/buttons in enclosure
Repeatability test: app sends values to microcontroller; Verify enclosure ergonomics
Prepare subsystem-level demo (app + microcontroller + enclosure); Photograph enclosure for report
Debug last app backend issues (simulation only); Document enclosure testing results
Dry-run subsystem demo; Finalize enclosure CAD drawings
Backup app + CAD files; Add diagrams/screenshots to report
Write subsystem testing summary; Assemble enclosure documentation package
Prepare final slides for subsystem demo
Demo rehearsal (subsystem only)
Freeze documentation content; Add final enclosure pictures/diagrams
Subsystem-wide test (app stubs + microcontroller + enclosure)
Fix last-minute bugs; Final cleanup of enclosure
Deliver final app subsystem, enclosure, and documentation package

## DACMicrocontroller
Item Description | 2025-08-25

## FPGAMemory
Item Description | 2025-08-25

## PowerFilter
Item Description | 2025-08-25