## Entire Team
Item Description | time axis 2025-08-25 to 2025-12-05
Complete SU 1 Slides | 2025-09-28: In Progress
SU Presention Run-Through | 2025-09-28: Not Started; 2025-09-30: Not Started
Status Update 1 Presentation | 2025-09-30: Due Date
Write FSR | 2025-09-28: Not Started; 2025-09-30: Not Started; 2025-10-02: Due Date
Write ICD | 2025-09-28: Not Started; 2025-09-30: Not Started; 2025-10-02: Due Date
Create Validation Plan | 2025-09-28: In Progress; 2025-09-30: In Progress; 2025-10-02: Due Date
ECEN Design Blitz | 2025-10-18: Due Date; 2025-10-20: Due Date
Complete SU 2 Slides | 2025-10-22: Not Started; 2025-10-24: Not Started; 2025-10-26: Not Started
SU Presention Run-Through | 2025-10-24: Not Started; 2025-10-26: Not Started
Status Update 2 Presentation | 2025-10-28: Due Date
Complete SU 3 Slides | 2025-11-13: Not Started; 2025-11-15: Not Started; 2025-11-17: Not Started
SU Presentation Run-Through | 2025-11-15: Not Started; 2025-11-17: Not Started
Status Update 3 Presentation | 2025-11-19: Due Date
Finial Report Due | 2025-12-05: Due Date
Mobile App/Enclosure | 2025-09-28: In Progress; 2025-09-30: Not Started; 2025-10-02: Not Started; 2025-10-04: Not Started; 2025-10-06: Not Started; 2025-10-08: Not Started; 2025-10-10: Not Started; 2025-10-12: Not Started; 2025-10-14: Not Started; 2025-10-16: Not Started; 2025-10-18: Not Started; 2025-10-20: Not Started
DAQ/Microcontrollers | 2025-09-28: Not Started; 2025-09-30: Not Started; 2025-10-02: Not Started; 2025-10-04: Not Started; 2025-10-06: Not Started; 2025-10-08: Not Started; 2025-10-10: Not Started; 2025-10-12: Not Started; 2025-10-14: Not Started; 2025-10-16: Not Started; 2025-10-18: Not Started; 2025-10-20: Not Started
FPGA/Memory | 2025-09-28: Not Started; 2025-09-30: Not Started; 2025-10-02: Not Started; 2025-10-04: Not Started; 2025-10-06: Not Started; 2025-10-08: Not Started; 2025-10-10: Not Started; 2025-10-12: Not Started; 2025-10-14: Not Started; 2025-10-16: Not Started; 2025-10-18: Not Started; 2025-10-20: Not Started
Power/Filtering | 2025-09-28: Not Started; 2025-09-30: Not Started; 2025-10-02: Not Started; 2025-10-04: Not Started; 2025-10-06: Not Started; 2025-10-08: Not Started; 2025-10-10: Not Started; 2025-10-12: Not Started; 2025-10-14: Not Started; 2025-10-16: Not Started; 2025-10-18: Not Started; 2025-10-20: Not Started

## MobileEclosure
Item Description | time axis 2025-08-25 to 2025-12-05
Not Started
Not Started
[18 empty] | Not Started | Not Started

## DACMicrocontroller
Item Description | time axis 2025-08-25 to 2025-12-05

## FPGAMemory
Item Description | time axis 2025-08-25 to 2025-12-05

## PowerFilter
Item Description | time axis 2025-08-25 to 2025-12-05